## Tasks
TaskID | ProjectID | WorkflowID | TaskName | Start Date | EndDate | Duration

## TasksDefined
TaskDefID | TaskName | TaskDescription | Startup Time | Shutdown Time | Cycletime | Units
1 | print packets |  |  |  | 3 | packets
2 | pull source bag |  |  |  | 10 | source bags
3 | treat seed (source bag) |  |  |  | 55 | source bags
4 | associate packets and sources |  |  |  | 10.955 | source bags
5 | agriculex change source |  |  |  | 85 | source bags
6 | agriculex pack packets |  |  |  | 16.3 | packets
7 | agriculex organize sleeve |  |  |  | 11 | sleeves
8 | agriculex clear out |  |  |  | 36 | source bags
9 | sorting sleeve exchange |  |  |  | 44 | sleeves
10 | plot order sorting |  |  |  | 10.955 | packets
11 | walk between sets |  |  |  | 25 | sets per sleeve
12 | QC set |  |  |  | 25 | sets
13 | QC packet |  |  |  | 1 | packets
14 | field order sorting |  |  |  | 10.955 | packets
15 | QC set |  |  |  | 25 | sets
16 | QC packet |  |  |  | 1 | packets
17 | palletize to field order |  |  |  | 25 | sets

## Dependencies
DependencyID | ProjectID | PredecessorTaskID | SuccessorTaskID | Type

## Assignements
AssignmentID | TaskID | ResourceID | WorkerID

## Projects
ProjectID | Project Name | WorkflowID | Start Date | EndDate | Packets | SourceBags | #ofSleeves | AvgSetsPerSleeve(sort) | #ofSets | Treated
1 | S24 Archive Packets | 1 |  |  | 13260 | 1 | 0.5 | 2 | 26.52 | no
2 | S24 Checks | 2 |  |  | 5700 | 15 | 15 | 1 | 5.7 | yes
3 | S24 Filler | 3 |  |  | 15000 | 6 | 6 | 1 | 15 | yes
4 | S24 YP Phase 1 Yield Trial | 4 |  |  | 1600 | 400 | 133.3333 | 3 | 8 | yes
5 | S24 YP Phase 2 Yield Trial | 4 |  |  | 792 | 66 | 33 | 2 | 3.96 | yes
6 | S24 Phase 1 Yield Trials | 4 |  |  | 24000 | 3000 | 1000 | 3 | 120 | yes
7 | S24 European Yield Trials | 5 |  |  | 400 | 25 | 25 | 1 | 2 | no
8 | S24 Discovery Active Learning - early maturity | 4 |  |  | 960 | 120 | 60 | 2 | 4.8241 | yes
9 | S24 Discovery Active Learning - sucrose | 4 |  |  | 960 | 120 | 60 | 2 | 4.8 | yes
10 | S24 YP Phase 4 Yield Trial | 4 |  |  | 240 | 12 | 12 | 1 | 1.2 | yes
11 | S24 YP Phase 3 Yield Trial | 4 |  |  | 440 | 22 | 22 | 1 | 2.2 | yes
12 | S24 TI HT Yield Trials | 4 |  |  | 4000 | 40 | 40 | 1 | 20 | yes
13 | S24 GE Yield Trials (Stewarded) | 4 |  |  | 600 | 15 | 15 | 1 | 3 | yes
14 | S24 Non-HT Yield Trials | 4 |  |  | 900 | 20 | 20 | 1 | 4.5 | yes
15 | S24 Phase 2 Yield Trials | 4 |  |  | 17000 | 600 | 600 | 1 | 85 | yes
16 | S24 Phase 3 Yield Trials | 4 |  |  | 5200 | 130 | 130 | 1 | 26 | yes

## Milestones
UID | MilestoneID | MilestoneName | Date
17 | 1 | S24 Yield Trial Packaging Start | 2025-01-01
18 | 2 | S24 YP Mataerial Received | 2025-03-01
19 | 3 | S24 YTP Finish | 2025-05-01

## Workflows
WorkflowID | WorkflowName
1 | archive packets
2 | check packets
3 | filler packets
4 | yield trial packaging (treated)
5 | yield trial packaging (not treated)

## WorkflowTasks
WorkflowTaskID | WorkflowID | TaskDefID | WorkFloPreID | WorkFlowSuccID
1 | 1 | 1 |  | 2
2 | 1 | 6 | 1 | 3
3 | 1 | 10 | 2 | 4
4 | 1 | 12 | 3 | 5
5 | 1 | 13 | 4
6 | 2 | 1 |  | 7
7 | 2 | 2 | 6 | 8
8 | 2 | 3 | 7 | 9
9 | 2 | 4 | 8 | 10
10 | 2 | 5 | 9 | 11
11 | 2 | 6 | 10 | 12
12 | 2 | 7 | 11 | 13
13 | 2 | 8 | 12 | 14
14 | 2 | 9 | 13 | 15
15 | 2 | 10 | 14 | 16
16 | 2 | 14 | 15
17 | 3 | 1 |  | 18
18 | 3 | 2 | 17 | 19
19 | 3 | 3 | 18 | 20
20 | 3 | 4 | 19 | 21
21 | 3 | 5 | 20 | 22
22 | 3 | 6 | 21 | 23
23 | 3 | 7 | 22 | 24
24 | 3 | 8 | 23 | 25
25 | 3 | 9 | 24 | 26
26 | 3 | 10 | 25 | 27
27 | 3 | 14 | 26
28 | 4 | 1 |  | 29
29 | 4 | 2 | 28 | 30
30 | 4 | 3 | 29 | 31
31 | 4 | 4 | 30 | 32
32 | 4 | 5 | 31 | 33
33 | 4 | 6 | 32 | 34
34 | 4 | 7 | 33 | 35
35 | 4 | 8 | 34 | 36
36 | 4 | 9 | 35 | 37
37 | 4 | 10 | 36 | 38
38 | 4 | 11 | 37 | 39
39 | 4 | 12 | 38 | 40
40 | 4 | 13 | 39 | 41
41 | 4 | 14 | 40 | 42
42 | 4 | 15 | 41 | 43
43 | 4 | 16 | 42 | 44
44 | 4 | 17 | 43
45 | 5 | 1 |  | 46
46 | 5 | 2 | 45 | 47
47 | 5 | 4 | 46 | 48
48 | 5 | 5 | 47 | 49
49 | 5 | 6 | 48 | 50
50 | 5 | 7 | 49 | 51
51 | 5 | 8 | 50 | 52
52 | 5 | 9 | 51 | 53
53 | 5 | 10 | 52 | 54
54 | 5 | 11 | 53 | 55
55 | 5 | 12 | 54 | 56
56 | 5 | 13 | 55 | 57
57 | 5 | 14 | 56 | 58
58 | 5 | 15 | 57 | 59
59 | 5 | 16 | 58 | 60
60 | 5 | 17 | 59

## Workers
WorkerID | Worker Name | Rate
1 | worker 1 | 25
2 | worker 2 | 25
3 | worker 3 | 25
4 | worker 4 | 25
5 | worker 5 | 25
6 | worker 6 | 25
7 | worker 7 | 25
8 | worker 8 | 25
9 | manager 1 | 40

## TaskWorkersReq
TaskWorkerReqID | TaskID | workersRequired
1 | 1 | 1
2 | 2 | 1
3 | 3 | 1
4 | 4 | 1
5 | 5 | 1
6 | 6 | 1
7 | 7 | 1
8 | 8 | 1
9 | 9 | 1
10 | 10 | 1
11 | 11 | 1
12 | 12 | 1
13 | 13 | 1
14 | 14 | 1
15 | 15 | 1
16 | 16 | 1

## Equipment
EquipmentID | Equipment Name | QuantityAvailable
1 | Treater | 3
2 | Packet Printer | 1
3 | Agriculex | 3

## TaskEquipmentReq
TaskEquipmentReqID | TaskID | EquipmentID
1 | 1 | 2
2 | 3 | 1
3 | 5 | 3
4 | 6 | 3
5 | 7 | 3
6 | 8 | 3

## ScheduleUIDs
UID | Project Name | ProjectID | MilestoneID | Predecessor | Successor
1 | S24 Archive Packets | 1
2 | S24 Checks | 2
3 | S24 Filler | 3
4 | S24 YP Phase 1 Yield Trial | 4
5 | S24 YP Phase 2 Yield Trial | 5 |  | 4
6 | S24 Phase 1 Yield Trials | 6 |  | 17
7 | S24 European Yield Trials | 7
8 | S24 Discovery Active Learning - early maturity | 8
9 | S24 Discovery Active Learning - sucrose | 9
10 | S24 YP Phase 4 Yield Trial | 10
11 | S24 YP Phase 3 Yield Trial | 11
12 | S24 TI HT Yield Trials | 12
13 | S24 GE Yield Trials (Stewarded) | 13
14 | S24 Non-HT Yield Trials | 14
15 | S24 Phase 2 Yield Trials | 15 |  | 6
16 | S24 Phase 3 Yield Trials | 16 |  | 15
17 | S24 Yield Trial Packaging Start |  | 1
18 | S24 YP Mataerial Received |  | 2
19 | S24 YTP Finish |  | 3