## ScheduleEvents
UID | EventType | EventID | PredecessorID | PredecessorType | PredDepType | SuccessorID | SuccessorType | SuccDepType | StartDate | EndDate

## Tasks
TaskID | ProjectID | WorkflowID | TaskName | StartDate | EndDate | Duration | WorkflowTaskID

## DependencyType
DependencyType
fs
ss
ff
sf

## ScheduleEventTypes
ScheduleEventType
task
project
milestone

## Milestones
MilestoneID | MilestoneName | Date
1 | S24 Yield Trial Packaging Start | 2025-01-01
2 | S24 YP Material Received | 2025-03-01
3 | S24 YTP Finish | 2025-05-01

## Projects
ProjectID | Project Name | WorkflowID | Start Date | EndDate | PredecessorID | PredecessorType | PredDepType | Packets | SourceBags | #ofSleeves | AvgSetsPerSleeve(sort) | #ofSets | Treated
1 | S24 Archive Packets | 1 |  |  | 1 | milestone |  | 13260 | 1 | 0.5 | 2 | 26.52 | no
2 | S24 Checks | 2 |  |  | 1 | project | fs | 5700 | 15 | 15 | 1 | 5.7 | yes
3 | S24 Filler | 3 |  |  | 2 | project | fs | 15000 | 6 | 6 | 1 | 15 | yes
4 | S24 YP Phase 1 Yield Trial | 4 |  |  | 3 | project | fs | 1600 | 400 | 133.3333 | 3 | 8 | yes
5 | S24 YP Phase 2 Yield Trial | 4 |  |  | 4 | project | fs | 792 | 66 | 33 | 2 | 3.96 | yes
6 | S24 Phase 1 Yield Trials | 4 |  |  | 5 | project | fs | 24000 | 3000 | 1000 | 3 | 120 | yes
7 | S24 European Yield Trials | 5 |  |  | 6 | project | fs | 400 | 25 | 25 | 1 | 2 | no
8 | S24 Discovery Active Learning - early maturity | 4 |  |  | 7 | project | fs | 960 | 120 | 60 | 2 | 4.8241 | yes
9 | S24 Discovery Active Learning - sucrose | 4 |  |  | 8 | project | fs | 960 | 120 | 60 | 2 | 4.8 | yes
10 | S24 YP Phase 4 Yield Trial | 4 |  |  | 9 | project | fs | 240 | 12 | 12 | 1 | 1.2 | yes
11 | S24 YP Phase 3 Yield Trial | 4 |  |  | 10 | project | fs | 440 | 22 | 22 | 1 | 2.2 | yes
12 | S24 TI HT Yield Trials | 4 |  |  | 11 | project | fs | 4000 | 40 | 40 | 1 | 20 | yes
13 | S24 GE Yield Trials (Stewarded) | 4 |  |  | 12 | project | fs | 600 | 15 | 15 | 1 | 3 | yes
14 | S24 Non-HT Yield Trials | 4 |  |  | 13 | project | fs | 900 | 20 | 20 | 1 | 4.5 | yes
15 | S24 Phase 2 Yield Trials | 4 |  |  | 14 | project | fs | 17000 | 600 | 600 | 1 | 85 | yes
16 | S24 Phase 3 Yield Trials | 4 |  |  | 15 | project | fs | 5200 | 130 | 130 | 1 | 26 | yes

## Workflows
WorkflowID | WorkflowName
1 | archive packets
2 | check packets
3 | filler packets
4 | yield trial packaging (treated)
5 | yield trial packaging (not treated)

## WorkflowTasks
WorkflowTaskID | WorkflowID | TaskDefID | WorkFloPreID | WorkFlowSuccID | PredDepType
1 | 1 | 1 |  | 2
2 | 1 | 6 | 1 | 3 | fs
3 | 1 | 10 | 2 | 4 | fs
4 | 1 | 12 | 3 | 5 | fs
5 | 1 | 13 | 4 |  | fs
6 | 2 | 1 |  | 7
7 | 2 | 2 | 6 | 8 | fs
8 | 2 | 3 | 7 | 9 | fs
9 | 2 | 4 | 8 | 10 | fs
10 | 2 | 5 | 9 | 11 | fs
11 | 2 | 6 | 10 | 12 | fs
12 | 2 | 7 | 11 | 13 | fs
13 | 2 | 8 | 12 | 14 | fs
14 | 2 | 9 | 13 | 15 | fs
15 | 2 | 10 | 14 | 16 | fs
16 | 2 | 14 | 15 |  | fs
17 | 3 | 1 |  | 18
18 | 3 | 2 | 17 | 19 | fs
19 | 3 | 3 | 18 | 20 | fs
20 | 3 | 4 | 19 | 21 | fs
21 | 3 | 5 | 20 | 22 | fs
22 | 3 | 6 | 21 | 23 | fs
23 | 3 | 7 | 22 | 24 | fs
24 | 3 | 8 | 23 | 25 | fs
25 | 3 | 9 | 24 | 26 | fs
26 | 3 | 10 | 25 | 27 | fs
27 | 3 | 14 | 26 |  | fs
28 | 4 | 1 |  | 29
29 | 4 | 2 | 28 | 30 | fs
30 | 4 | 3 | 29 | 31 | fs
31 | 4 | 4 | 30 | 32 | fs
32 | 4 | 5 | 31 | 33 | fs
33 | 4 | 6 | 32 | 34 | fs
34 | 4 | 7 | 33 | 35 | fs
35 | 4 | 8 | 34 | 36 | fs
36 | 4 | 9 | 35 | 37 | fs
37 | 4 | 10 | 36 | 38 | fs
38 | 4 | 11 | 37 | 39 | fs
39 | 4 | 12 | 38 | 40 | fs
40 | 4 | 13 | 39 | 41 | fs
41 | 4 | 14 | 40 | 42 | fs
42 | 4 | 15 | 41 | 43 | fs
43 | 4 | 16 | 42 | 44 | fs
44 | 4 | 17 | 43 |  | fs
45 | 5 | 1 |  | 46
46 | 5 | 2 | 45 | 47 | fs
47 | 5 | 4 | 46 | 48 | fs
48 | 5 | 5 | 47 | 49 | fs
49 | 5 | 6 | 48 | 50 | fs
50 | 5 | 7 | 49 | 51 | fs
51 | 5 | 8 | 50 | 52 | fs
52 | 5 | 9 | 51 | 53 | fs
53 | 5 | 10 | 52 | 54 | fs
54 | 5 | 11 | 53 | 55 | fs
55 | 5 | 12 | 54 | 56 | fs
56 | 5 | 13 | 55 | 57 | fs
57 | 5 | 14 | 56 | 58 | fs
58 | 5 | 15 | 57 | 59 | fs
59 | 5 | 16 | 58 | 60 | fs
60 | 5 | 17 | 59 |  | fs

## TasksDefined
TaskDefID | TaskName | TaskDescription | Startup Time | Shutdown Time | Cycletime | Units
1 | print packets |  |  |  | 3 | Packets
2 | pull source bag |  |  |  | 10 | SourceBags
3 | treat seed (source bag) |  |  |  | 55 | SourceBags
4 | associate packets and sources |  |  |  | 10.955 | SourceBags
5 | agriculex change source |  |  |  | 85 | SourceBags
6 | agriculex pack packets |  |  |  | 16.3 | Packets
7 | agriculex organize sleeve |  |  |  | 11 | #ofSleeves
8 | agriculex clear out |  |  |  | 36 | SourceBags
9 | sorting sleeve exchange |  |  |  | 44 | #ofSleeves
10 | plot order sorting |  |  |  | 10.955 | #ofSleeves
11 | walk between sets |  |  |  | 25 | AvgSetsPerSleeve(sort)
12 | QC set |  |  |  | 25 | #ofSets
13 | QC packet |  |  |  | 1 | Packets
14 | field order sorting |  |  |  | 10.955 | Packets
15 | QC set |  |  |  | 25 | #ofSets
16 | QC packet |  |  |  | 1 | Packets
17 | palletize to field order |  |  |  | 25 | #ofSets